## Sheet1
Date | Resource | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
2024-06-17 | Sankar Pratap Samanta | Work on training and course module bug fixing | Work on training and course module bug fixing | Work on training and course module bug fixing | Work on training and course module bug fixing | Work on training and course module bug fixing | Work on training and course module bug fixing | Work on training and course module bug fixing | Deployment the codes to the server with anu mam
2024-06-17 | Priyanka
2024-06-18 | Sankar Pratap Samanta | Working on E-Office module bug fixing for SLI project | Working on E-Office module bug fixing for SLI project | Working on E-Office module bug fixing for SLI project | Working on E-Office module bug fixing for SLI project | Working on E-Office module bug fixing for SLI project | Working on E-Office module bug fixing for SLI project | Working on E-Office module bug fixing for SLI project | Working on E-Office module bug fixing for SLI project
2024-06-18 | Priyanka | 1: Working on; 2: Working on Workshop module bug fixing for SLI project; 7: Working on RnP module bug fixing for SLI project |  | Working on RnP module bug fixing for SLI project
2024-06-19 | Sankar Pratap Samanta | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team | Work on remaining bug fiixing for training , course and finance module , Report given by QA Team
2024-06-19 | Priyanka | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing
2024-06-20 | Sankar Pratap Samanta | Work on E-office module bug issues | Work on E-office module bug issues | Work on E-office module bug issues | Work on E-office module bug issues | Work on E-office module bug issues | Work on E-office module bug issues | Work on E-office module bug issues | Take KT form Saiket for People-O project
2024-06-20 | Priyanka | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing | Work on e-office bug fixing